ROYAL BRITISH LEGION

DERBYSHIRE COUNTY PLAN

(2025 – 2028)

# 1. INTRODUCTION AND BACKGROUND

This County Plan is intended to record planned objectives for the next three years.  The plan was agreed by the County Committee at its meeting held on 5th October 2024, reviewed in April/May 2025 and updated following the launch of the 2025-2035 Strategy.

Input:

Survey carried out and details shared through the Monthly Newsletter and the County Committee members were asked for input at the meetings in April and July.

Reformatted following launch of Our Strategy 2025-2035.

| Completed | In progress | Not started | New |
| --- | --- | --- | --- |

# 2. OUTCOMES – Our Strategy 2025-2035

| # Connect | # Remember | # Support |
| --- | --- | --- |
| The Armed Forces community have more and better opportunities to connect and come together. Connections are created and sustained across communities to understand and support the Armed Forces community | The Armed Forces community feel that their service and sacrifice is values and recognised. People acknowledge the service and sacrifice of the Armed Forces community and participate in Remembrance. | The Armed Forces community are receiving the services and support that they need. |
| Underpinned by good Governance, Administration, Finance, Safeguarding and Safety |  |  |

Connect

| Sub Committee/ Team | Objective | Progress | Target date | Achievement Date | Responsibility | Key Performance Indicator(s) |
| --- | --- | --- | --- | --- | --- | --- |
| Growth and Development | Recruit a County Recruiting Officer | Completed | Oct 2024 | April 2025 | County Chair | County Recruiting Officer in post and has a clear role description |
| Growth and Development | All current members are briefed in ‘elevator talk’, What is the RBL? | Completed | May 2025 | May 2025 | County Chair | 3% grow on annual membership. |
| Growth and Development | Recruit a Recruiting team of 2 recruitment advisers | Advert out in April 2025 | Oct 2025 |  | County Recruiting Officer | Recruitment advisers are in post and actively engage with branches to support growth. |
| Growth and Development | Grow the county by a minimum of 3% grow on annual membership. | Target to be reviewed | Dec 2026 |  | County Recruiting Officer | County membership grows. Growth on all Branch Meeting Agendas. The county grows for 5 consecutive years |
| Growth and Development | Members are retained by: High quality Branch meetings offered Branches appoint a Membership Secretary Members are welcomed to meetings and events through a team of designated branch members | Beacon Branch Scheme to be explored with Branches and support Development Planning, | July 2025 |  | County Chair | 3% grow on annual membership. |

| Sub Committee/ Team | Objective | Progress | Target date | Achievement Date | Responsibility | Key Performance Indicator(s) |
| --- | --- | --- | --- | --- | --- | --- |
| Growth and Development Training | Recruit a County Training Officer | Completed | Oct 2024 | Oct 2024 | County Chair | CTO in role and has completed appropriate training for the role. |
| Growth and Development Training | All County Committee and potential County Committee members to attend the County Management Course | Completed | Dec 2024 | Mar 2025 | County Training Officer | To be recorded on Discover |
| Growth and Development Training | Arrange quarterly Branch Management Training Course within the County. | Planning underway | Dec 2025 |  | County Training Officer | CTO reports to the County Committee. |
| Growth and Development Training | Positive relationship with the Learning and Development Team established. | Requests made for Q1/ Q2 Annual training calendar to be developed | Jan 2026 |  | County Training Officer | Training delivered within the county and L&D Team meets the needs of members in Derbyshire |
| Growth and Development Training | Arrange two Branch Officer Seminars per year that are attended by 75% of branches | Seminars held but engagement to be developed | Oct 2025 |  | County Chair | Report to County Committee |
| Growth and Development Training | All Branches have a development plan in place. |  | Dec 2025 |  | County Committee | Branches have support from County Committee members. Branch AGMs are attended by a County Committee member. Branch Plan development is supported by a member of the County Committee. |

Remember

| Sub Committee/ Team | Objective | Progress | Target date | Achievement Date | Responsibility | Key Performance Indicator(s) |
| --- | --- | --- | --- | --- | --- | --- |
| Ceremonial | To participate in events across the county and represent the RBL |  | Dec 2025 |  | County Chair | Civic, community and armed forces events know and part of the annual calendar. |
| Ceremonial | To carry out Standard Bearer training across the county |  | Dec 2025 |  | County Parade Marshall | Annual calendar of training/ competition planned in advance by Dec for the following year. Report to County Committee |
| Ceremonial | Arrange and hold County Standard Bearer Competition. |  | Oct 2025 |  | County Parade Marshall | County Standard Bearer advised for Regional Competition. |
| Ceremonial | Increase the participation of branch standard bearers in the annual County Standard Bearer Competition. |  | Oct 2025 |  | County Parade Marshall | County Parade Marshall to report to the County Committee each May. |
| County Committee | To assist and support the Poppy Appeal |  | June 2026 |  | County Chair | Poppy Appeal Manager to report to County Committee overview. |

Support

| Sub Committee/ Team | Objective | Progress | Target date | Achievement Date | Responsibility | Key Performance Indicator(s) |
| --- | --- | --- | --- | --- | --- | --- |
| Outreach Branch Community Support | Appoint a County Community Support Officer | Completed | Oct 2024 | April 2025 | County Chair | County Community Support Officer in role and completed training |
| Outreach Branch Community Support | Ensure that funds from the County and Welfare Accounts are available when requested by Central Grants for quarterly almonisation. | Completed | Dec 2024 | April 2025 | County Treasurer | Information to be included within report to County Committee at each meeting. |
| Outreach Branch Community Support | To get to 75% of all Derbyshire branches signed up to BCS. CCSO will visit branches without BCS and explain the programme. | 10 more members trained for BCS | July 2025 |  | County Community Support Officer | BCS returns show number of BCS Reps increasing year on year. |
| Outreach Branch Community Support | BCS will feel supported through meeting twice a year with CCSO |  | Dec 2025 |  | County Community Support Officer | BCS Reps to discuss common challenges and plans for ensuring all areas are covered in the county |
| Outreach Branch Community Support | Grow the support to local veterans through publicising the BCS. |  | Dec 2024 |  | County Community Support Officer | A BCS development plan will be in place. |

| Sub Committee/ Team | Objective | Progress | Target date | Achievement Date | Responsibility | Key Performance Indicator(s) |
| --- | --- | --- | --- | --- | --- | --- |
| Outreach | Publish Branch details on County Web Site | Completed | Dec 2024 | April 2025 | County Web Master | Website up to date and reviewed quarterly |
| Outreach | Ensure all branches are participate in the youth affiliation scheme | County Committee are aware of current affiliations. | Dec 2024 |  | County Youth Officer | All Branches have affiliated units. CYO has met with all Lead Volunteers of the Cadets. A programme is developed that branches are aware of that they could deliver |
| Outreach | The members in Derbyshire feel proud, empowered and valued by the RBL Derbyshire County Committee. |  | Dec 2025 |  | County Chair | Opportunities are planned and delivered to share good practice, support branches that are struggling and celebrate the successes we can learn from. Improved communication between the county committee and branches across the county. |
| Outreach | Appoint County Media Team Leader |  | Oct 2025 |  | County Chair | County Media Team Leader role description created and person appointed. |
| Outreach | RBL Brand recognised across the county |  | Dec 2025 |  | County Media Team Leader | Social Media channels are established. RBL join details are shared monthly within the local community through various challenges, Radio, online, print at events, Work alongside the Armed Forces Champions to reach all veterans |
| Outreach | Appoint a County Youth Officer |  |  |  | County Chair | County Youth Officer in role |

Governance

|  | Objective | Progress | Target date | Achievement Date | Responsibility | Key Performance Indicator(s) |
| --- | --- | --- | --- | --- | --- | --- |
| County Committee | Progress of the County and Branches are reviewed |  | July 2025 | April 2025 | County Chair | County Plan in place and reviewed at each County Committee meeting. County Committee members support Branches to develop a Plan. These are shared with the County Committee and support is identified where needed. |
| County Committee | County committee is efficient and effective in is operation |  | Dec 2024 | April 2025 | County Chair | Skills audit completed. Declaration of interests held by County Secretary. Clear plan and knowledge of terms of office. Review County Committee and develop County Team to support operational activities. |
| County Committee | Risk Register in place and risks mitigated |  | Dec 2024 |  | County Chair | Risk Register developed |
| County Committee | Safety and risk management appropriate to support operational activities. |  | Dec 2024 |  | County Chair | Safety Lead appointed on the Committee. Risk assessments developed for regular activities External review of risk management Emergency contacts and management are in place |
| County Committee | Young adults (18-30) are supported to fulfil roles as part of the County Team and Committee. |  | Feb 2026 |  | County Chair | Two members aged 18-30 elected as committee/ sub committee members |
| County Committee | Safeguarding |  |  |  | County Chair |  |
| County Committee | County Conference |  | Jan 2026 |  | County Chair |  |